## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
TEAM NAME | (Fill your team name here)
PROJECT NAME | (Fill your project name here)
PROJECT MENTOR | (Put your Mentor name here)
TEAM MEMBERS | Team Mamber Name 1
Team Member Name 2
Team Member Name 3
Team Member Name 4
Team Member Name 5

## Team_Status
TEAM NAME | SSAD01
PROJECT NAME | Plugin for RobusTest
PROJECT MENTOR | Venumadhav
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 5 -6
Learn Java and usage of Intellij | Preparation | Self | 4 |  | Done | Using IDEs can make our job easier
Role preferences | Coordination | Vinay | 0.5 | 0.3 | Done |  | 0.2 | 66.6667
Setting up Intellij | Preparation | Self | 1 | 1.5 | Done |  | -0.5 | 33.3333
Discuss bug report software | Preparation | Sai ragh | 1.5 | 0 | Done | This is critical to project success | 1.5
Develop questions for requirements elicitation | Documentation | Srikar | 5 |  | Done | Make sure scoping questions are included
Plugin features | Preparation | Vinay | 1.5 | 1 | Done |  | 0.5 | 50
Research existing technology | Preparation | Srikar | 2 | 1.5 | Done |  | 0.5 | 33.3333
Project synopsis writeup | Documentation | Sai ragh | 2 |  | Done
Identify role owners | Preparation | Sai ragh | 1 | 0.6 | Done | Multiple roles are OK - think about role & reponsibility distribution | 0.4 | 66.6667
Team Meeting | Coordination | Vinay | 1 | 2 | Done |  | -1 | 50
Status tracker | Documentation | Srikar | 1 |  | Done
Week 7-8
Creating a basic Plugin in java | Preparation | Vinay |  |  | Done
Getting familiar with Action class | Preparation | Self |  |  | Done
Team Meeting | Coordination | Sai ragh |  |  | Done
Status tracker | Documentation | Srikar |  |  | Done
Week 9-10
User verification | Preparation | Vinay |  |  | Done
Url Input and processing | Preparation | Sai ragh |  |  | Done
Team Meeting | Coordination | Self |  |  | Done
Status tracker | Documentation | Srikar |  |  | Done
Week 11-12
Fetching information from Server | Preparation | Sai ragh |  |  | Done
SQL scout plugin usage | Preparation | Srikar |  |  | Done
Team Meeting | Coordination | Vinay |  |  | Done
Discuss error with scout plugin | Preparation | Srikar |  |  | Done
Status tracker | Documentation | Vinay |  |  | Done
Week 12-13
Running VNC java viewer | Preparation | Srikar |  |  | Done
Rendering web view | Preparation | Sai ragh |  |  | Done
Team Meeting | Coordination | Vinay |  |  | Done
Discuss errors encountered | Preparation | Self |  |  | Done
Status tracker | Documentation | Sai ragh |  |  | Done
Week 14-15
NoVNC usage and comaptibility | Preparation | Srikar |  |  | Done
Connecting viewer and web view | Preparation | Sai ragh |  |  | Done
Team Meeting | Coordination | Vinay |  |  | Done
Discuss errors encountered | Preparation | Self |  |  | Done
Status tracker | Documentation | Vinay |  |  | Done
Week 16-17
Working of each module | Preparation | Srikar
Connecting two modules | Preparation | Sai ragh
Integration of all modules | Preparation | Vinay
Team Meeting | Coordination | Sai ragh
Discuss errors encountered | Preparation | Vinay
Status tracker | Documentation | Srikar
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically

## Individual_Status
TEAM NAME | (Fill your team name here)
PROJECT NAME | (Fill your project name here)
PROJECT MENTOR | (Put your Mentor name here)
Actvities | Team Mamber Name 1 |  | Team Member Name 2 |  | Team Member Name 3 |  | Team Member Name 4 |  | Team Member Name 5 |  | Estimated Total Hours | Actual Total Hours
| Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent
Week 5 -6
Learn Java and usage of Intellij | [10 empty] | 0 | 0
Role preferences | [10 empty] | 0 | 0
Setting up Intellij | [10 empty] | 0 | 0
Discuss bug report software | [10 empty] | 0 | 0
Develop questions for requirements elicitation | [10 empty] | 0 | 0
Plugin features | [10 empty] | 0 | 0
Research existing technology | [10 empty] | 0 | 0
Project synopsis writeup | [10 empty] | 0 | 0
Identify role owners | [10 empty] | 0 | 0
Team Meeting | [10 empty] | 0 | 0
Status tracker | [10 empty] | 0 | 0
Week 7-8
Creating a basic Plugin in java | [10 empty] | 0 | 0
Getting familiar with Action class | [10 empty] | 0 | 0
User verification | [10 empty] | 0 | 0
Url Input and processing | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
Week 9-10
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
Team Meeting | [10 empty] | 0 | 0
Week 11-12 | [10 empty] | 0 | 0
Fetching information from Server | [10 empty] | 0 | 0
Team Meeting | [10 empty] | 0 | 0
Week 12-13 | [10 empty] | 0 | 0
Running VNC java viewer | [10 empty] | 0 | 0
Rendering web view | [10 empty] | 0 | 0
Discuss errors encountered | [10 empty] | 0 | 0
Week 14-15 | [10 empty] | 0 | 0
NoVNC usage and comaptibility | [10 empty] | 0 | 0
Connecting viewer and web view | [10 empty] | 0 | 0
Discuss errors encountered | [10 empty] | 0 | 0
Week 16-17 | [10 empty] | 0 | 0
Working of each module | [10 empty] | 0 | 0
Connecting two modules | [10 empty] | 0 | 0
Integration of all modules | [10 empty] | 0 | 0
Team Meeting | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
#REF! | [10 empty] | 0 | 0
Discuss errors encountered | [10 empty] | 0 | 0
Status tracker | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0

## Compatibility Report
Compatibility Report for StatusTracker-1.xls
Run on 31-10-2016 22:17
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 1