## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

PROJECT NUMBER	(Fill your Project Number here)
PROJECT NAME	(Fill your project name here)
PROJECT MENTOR (sponsor)	(Put your Project Mentor (sponsor) name here)
TEAM MEMBERS	Team Mamber Name 1
	Team Member Name 2
	Team Member Name 3
	Team Member Name 4
	Team Member Name 5

## Status
PROJECT NUMBER	SSAD50
PROJECT NAME	ROBUS TEST PLUGIN DEVELOPMENT
PROJECT MENTOR (sponsor)	AISHWARYA MISHRA

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 1 (August 8- August 14)
Fix meeting with client	Coordination	VINAY	0.2	0.1	Done		0.1	100
GIT Repository setup	Preparation	TA	0	0	Done		0
Client meeting	Coordination	SRIKAR	2	1	Done	discussed slightly about the project and their company	1	100
Client meet2	Design	SAIRAGH	2	1.5	Done	discussed about their company completely and they make sure us to know about their functioning	0.5	33.3333333333
Project synopsis writeup	Documentation	SAIRAGH	0.5	0.5	Done	Wrote all about what discussed in the client meets means basically project description	0	0
Team Meeting	Coordination	ALL	1	2	Done	Discussion about how to learn java in easy way and explicitly discussed about the terms which were used in meets	-1	50
Mail regarding Client meets	Requirements	VINAY	0.5	0.5	Done	Got mail regarding java tutorial and some basic terms regarding the project	0	0